## Backlog
ID | Section | Feature | Description | Ref | Status | Effort | Code Group | Cross-links | Priority | Comments
1 | Creative Tools | Bitmap sprite render path | Teach the engine to draw an arbitrary frame-sheet image as any sprite (player/enemy/item/block). The missing backend both the paint tool and the importer sit on. | C(§13) | Not started | L | A | F
2 | Creative Tools | Part Studio (Rungs 2-3) | Beginner-first editor: reshape by sliders (no drawing) + paint your own parts that the skeleton skins & animates. Live animated preview, mirror-draw, fork-a-preset. | E1(§13) | Not started | L | A | D
3 | Creative Tools | Exported animation template | Drive the stick figure through every supported pose and export the frames as a reference sheet that matches real game timing. | D(§13) | Not started | M | A
4 | Creative Tools | Ghost-draw animation guide | The exported frames shown faded behind the raster so new animators trace real motion. Enable/disable; never saved. | F(§13) | Not started | M | A | D
5 | Creative Tools | Frame Studio (Rung 4) | Full frame-by-frame pixel editor for skilled creators; only path for static items/blocks and non-humanoid sprites. | E2(§13) | Not started | L | A | D
6 | Creative Tools | Sprite-sheet importer | The 'Import Sprite Sheet' button the how-to guide promises: PNG upload -> slice -> preview -> save, rendered via the bitmap render path. | G(§13) | Not started | M | A | D
7 | Creative Tools | Enemy model templates | Library of movement+style presets (spider gait, hopper, flyer) a creator reskins - custom enemies without touching AI. Extends to a shareable model library. | E3(§13) | Not started | L | A | C
8 | Creative Tools | Movement Editor (keyframe poses) | Pose the stick figure into ~10 keyframes + speed; engine tweens the joints. Emotes/dances feasible; new mechanics separate; never changes hitbox. FAR FUTURE. | H(§13) | Far future | XL | A | B
9 | Progression & meta | Progression-gated creation | Achievements unlock creator power; the accessibility ladder IS the unlock tree. Creative-vs-Progression mode, never gate basics, aspirational locks. | §14 | Planned | XL | E | D
10 | Progression & meta | Per-account unlock ledger | The one missing DB piece for the above - a per-account achievement/unlock table + unlock-check at each gated feature (Epic D's per-world ledger is the pattern). | §14 | Not started | M | E | D
11 | Major modes | Tower Defense mode | Dedicated wave-survival: mobs advance a route toward a core; place/upgrade towers on an emerald economy; survive N waves. Distinct from Arena 'Defend the Tower'. | §11 | Not started | XL | E | C
12 | Major modes | TD/MOBA substrate + tiered bot-AI | The larger action-strategy layer: lanes, team-aware targeting, smarter cross-mode bots. Ambitious, shared substrate for TD + MOBA. | §4 | Not started | XL | E | C
13 | Major modes | Campaign: manual save / checkpoints | Deferred from the Campaign MVP - let players save mid-campaign / checkpoint progress. | §28 | Not started | M | E
14 | Major modes | Campaign: multi-user publishing + selection UI | Deferred from the Campaign MVP - publish a campaign for others + a selection/browse UI. | §29 | Not started | M | E | G
15 | Major modes | Warden boss + platformer boss pass | New heavy boss (Warden vein) + a broader Platformer boss pass. Reuses Wither/Dragon boss infra (HP bar, scaling multipliers). | §10 | Not started | M | C | E
16 | Onboarding & platform | User Guide | Per-mode HTML help pages (Normal/Platformer/Speed Run/Sandbox/Arena). Sandbox+Arena are the long ones (scattered shortcut trace-and-verify). | §1 | Not started | M | G | D
17 | Onboarding & platform | Dedicated per-mode front-ends | speedrun.html / platformer.html that boot straight into a curated, editor-free mode experience + leaderboard. Same accounts/DB underneath. | front-ends | Deferred | M | G
18 | Onboarding & platform | Designer / 'God' mode settings tier | Hide advanced world-settings behind a Designer toggle so normal players see a short clean list; reveal all 'advanced' rows when on. | god-mode | Not started | S | D
19 | Onboarding & platform | Desktop installer (itch.io / Tauri) | Signed .exe/.dmg or store listing wrapping the same web app. PWA already covers browser install. | §8 | Not started | M | G
20 | Onboarding & platform | Offline providers: Normal/Platformer/Arena | Extend the localStorage offline provider beyond Sandbox so the other modes work offline too. | §6 | Partial | M | G | E
21 | Onboarding & platform | Full controls-config capture UI | Arbitrary key/button rebinding (foundation shipped; capture UI deferred). Plus a touch-controls On/Off/Auto toggle. | §19 | Partial | M | D | G
22 | Combat & movement | Player/designer-created combos | Let players/designers define their own input-sequence combos (combos.js COMBOS.DEFS schema already supports it). | combat | Not started | M | B | D
23 | Combat & movement | Combo testing gym | Practice space to drill combos + where designers verify a custom combo is executable and feels good. | combat | Not started | M | B
24 | Combat & movement | Jump attack (air melee) | Melee variant during a jump - likely normal-jump and air/double-jump variants. Slots alongside the directional-melee system. | combat | Not started | S | B
25 | Combat & movement | Directional-melee per-weapon animations | Mechanics shipped (targeting/dodge/damage); distinct per-direction/per-weapon swing ART is the flagged follow-up. | combat | Not started | M | A | B
26 | Combat & movement | Grapple polish | Reuse the real ledge-climb anim for the 1-block climb-over; optional cable-vs-terrain collision; feel-tune the swing. | combat | Not started | M | B | A
27 | Combat & movement | Held-boomerang / held-grapple sprites | Both currently fall back to the generic melee/ranged draw. | combat | Not started | S | A
28 | Combat & movement | Item Enchantment system | Composable attack traits granted via enchantments (e.g. crossbow piercing -> generic trait applied to other weapons). | §17 | Not started | M | B
29 | Mobs & AI | Wayfinding & ambush-from-above | The last Smart-Mobs piece: mobs path intelligently (tile A*/navmesh) and ambush from above. | §6 | Not started | L | C
30 | Mobs & AI | Mob Variety / Config engine | Designers choose which mobs a world supports + tune per-mob params; selected mobs become spawn eggs / config options. | §16 | Not started | L | C | D
31 | Mobs & AI | Suspicion / alert meter | Accumulating detection meter per mob (partial sight/faint sound) that decays - more forgiving than today's instant trigger. | §18 | Not started | M | C
32 | Mobs & AI | Bot navigation: doors & crawl gaps | Let bots open doors and path through 1-block crawl gaps. | §21 | Not started | M | C | F
33 | Mobs & AI | Companion stuck retry + follow cues | When the companion repeats a failed maneuver, try a different approach before the '!'; add a visual cue for follow/repeat mode. | §22 | Not started | S | C
34 | Overhead engine | Directional pistons + articulated gates | Deferred runtime: vertical elevator + horizontal push pistons (sticky, auto-stack, entity push) + a configurable swinging gate. | pistons | Not started | L | F
35 | Overhead engine | Doors + chests | Keys/locks shipped; doors + chests deferred (key-driven puzzles). | §38 | Not started | M | F
36 | Overhead engine | Underground / cave mode | Negative elevations vs a separate cave map; optionally seamless surface<->cave in one world. | §35 | Not started | L | F
37 | Overhead engine | End portals | Overhead End-dimension portals. | §35 | Not started | M | F | E
38 | Overhead engine | NPCs / villagers | Non-hostile NPCs (dialogue/quests/trade groundwork). | §30 | Not started | L | F | C
39 | Overhead engine | Skin / prefab / structure builder | Overhead building & sprite skin builder, now also the prefab/structure creator. | §31 | Not started | L | F | A
40 | Overhead engine | Editor clipboard + more paint tools | Selection/clipboard (copy/paste regions) + more painting tools in the overhead editor. | §37 | Not started | M | F | D
41 | Overhead engine | Scale-model authoring tiers | Canonical scale-model + authoring tiers spec (supersedes scale bits of earlier notes). | §39 | Not started | L | F
42 | Content tooling | Image-to-block converter | Drop an image, get a block mosaic in a world. | §27 | Not started | M | D | A
43 | Content tooling | Native screen capture | In-app capture for sharing worlds/runs. | §26 | Not started | S | G
44 | Content tooling | World cleanup widget | 'Manage Worlds' bulk cleanup (provenance dependency shipped). | §7 | Not started | S | D | G
45 | Content tooling | Background transition-zone editor | Tier 3: generalize hardcoded depth/column thresholds into designer-editable transition zones. | §9 | Not started | M | D
46 | Content tooling | Game Designer wizard / disaster-check | Expand the disaster-check tool (first two checks exist) into a fuller authoring wizard. | §25 | Partial | M | D
47 | Co-op & social | Platformer/Normal co-op UX redesign | Rework co-op entry/UX; deferred until the dashboard/landing rebuild. | §23 | Deferred | M | G | D
48 | Co-op & social | Companion / co-op selection UI placement | Where/how players pick a companion or co-op partner (placement flagged). | §20 | Not started | S | G | D
49 | Co-op & social | Online / MP UX direction | Broader online/multiplayer UX direction (lobbies, presence, invites) - discussion captured, not built. | §15 | Not started | L | G | E

## Legend
Code Group | Area | Primary files it touches
A | Sprite / character rendering & Creative Tools | player.js draw path, characters.js, js/overhead draw, the new sprite/part editor
B | Combat & movement mechanics | player.js physics/attacks, combos.js, weapons/traits
C | Mobs & AI | mobs.js, bot-ai.js, pathfinding / navmesh
D | Editor, world-settings & designer tooling | sandbox-ui.js, world-settings-ui.js, editor overlays
E | Game modes, progression & server | game.js mode logic, server/*routes.js, Supabase / SQL
F | Overhead engine | js/overhead/* (runtime + editor)
G | Front-end, onboarding, platform & distribution | index.html, dashboard.js, new HTML pages, PWA / Tauri
Effort | S = small (hours) ¦ M = medium (~a session) ¦ L = large (multi-session) ¦ XL = major initiative
Status | Not started / Planned (design agreed) / Partial (foundation shipped) / Deferred / Far future
How to use | Sort by Code Group to batch work that touches the same code (efficient); Cross-links shows a secondary area a task also touches. Fill Priority + Comments.